## Dashboard
Migration Budget Dashboard (NAM ↔ APAC)
High-level Cost Summary |  | Support Model by Product
Item | USD | Product | Monthly Tickets | Support Hrs/Month | Annual Cost (USD)
Labor Subtotal
Infrastructure Subtotal
Support (Annual)
Contingency (15%)
Estimated Total Budget

## Migration Budget Estimate
Atlassian Products Regional Migration Budget Estimate (NAM ↔ APAC)
Scope Summary
Products | Regions | Migration Type | Data Volume | Users | Notes
Jira Software | NAM → APAC | Cloud → Cloud | 500 GB | 300 | Wealth-related projects
Confluence | NAM → APAC | Cloud → Cloud | 300 GB | 300 | Spaces & attachments
Bitbucket | NAM → APAC | Cloud → Cloud | 200 GB | 200 | Repos & pipelines
Jira Software | APAC → NAM | Cloud → Cloud | 400 GB | 250 | Franchise-related projects
Confluence | APAC → NAM | Cloud → Cloud | 250 GB | 250 | Spaces & templates
Bitbucket | APAC → NAM | Cloud → Cloud | 150 GB | 150 | Repos & scripts
Role | Hours | Hourly Rate (USD) | Cost (USD)
Atlassian Admin | 120 | 70
Project Manager | 40 | 65
QA Engineer | 30 | 55
Network/Security Engineer | 25 | 60
Consulting Partner | 40 | 200
Subtotal
Support Cost Estimate (Based on Historical Defects/Requests)
Category | Quantity | Unit Cost (USD) | Total (USD) | Notes
Data Transfer (1.8 TB) | 1843 GB | 0.08 |  | AWS egress
Temp Storage | 1.8 TB | 0.03 |  | 1 month S3/Blob
Licensing delta | 550 users | 10 |  | Tax & regional cost
Downtime/Test |  | 800 | 800 | Verification effort
Subtotal
Contingency and Total
Product | Avg. Monthly Tickets | Support Hours/Month | Hourly Rate | Monthly Cost (USD) | Annual Cost (USD)
Jira | 120 | 40 | 70
Confluence | 80 | 25 | 70
Bitbucket | 60 | 20 | 70
Subtotal (Annual)
Item | Value (USD) | Notes
Labor + Infra subtotal
Support (annual)
Contingency (15%)
Estimated Total Budget

## WBS
WBS ID | Phase | Task Description | Owner | Estimated Hours | Cost (USD) | Dependencies
1.0 | Initiation | Define migration scope and objectives | Project Manager | 8 | 520
1.1 | Planning | Develop migration plan & timeline | Project Manager | 16 | 1040 | 1.0
1.2 | Planning | Assess current environments and data volume | Atlassian Admin | 20 | 1400 | 1.1
2.0 | Execution | Set up target environment (APAC & NAM) | Network/Security Engineer | 24 | 1440 | 1.2
2.1 | Execution | Migrate Jira projects (Wealth & Franchise) | Atlassian Admin | 40 | 2800 | 2.0
2.2 | Execution | Migrate Confluence spaces | Atlassian Admin | 30 | 2100 | 2.0
2.3 | Execution | Migrate Bitbucket repositories | Atlassian Admin | 25 | 1750 | 2.0
3.0 | Testing | Perform data validation and user acceptance | QA Engineer | 24 | 1320 | 2.1,2.2,2.3
3.1 | Testing | Reconnect integrations (CI/CD, SSO, APIs) | Network/Security Engineer | 20 | 1200 | 3.0
4.0 | Closure | Post-migration review and documentation | Project Manager | 16 | 960 | 3.1
4.1 | Closure | Training and handover to support | Consultant | 16 | 3200 | 4.0

## Cost Baseline
Week | Planned Value (PV) | Actual Cost (AC) | Earned Value (EV)
Week 1 | 2000 | 1800 | 1500
Week 2 | 5000 | 5200 | 4500
Week 3 | 9000 | 9400 | 8500
Week 4 | 14000 | 14200 | 13800
Week 5 | 18000 | 18500 | 18000
Week 6 | 22000 | 21500 | 22000
Week 7 | 26000 | 25800 | 26000
Week 8 | 28000 | 27900 | 28000

## Risk Register
Risk ID | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Owner | Status
R1 | Data loss during migration | High | High | 9 | Perform backups & test restores before migration | Atlassian Admin | Open
R2 | Unexpected downtime beyond window | Medium | High | 6 | Plan maintenance window; notify users early | Project Manager | Open
R3 | Integration failures post-move | High | Medium | 6 | Document integrations; retest all endpoints | Network Engineer | Open
R4 | License cost variation by region | Medium | Low | 3 | Pre-align finance with Atlassian billing team | Finance Lead | Mitigated
R5 | Compliance issues (PII/GDPR) | Low | High | 3 | Review with compliance; ensure data residency adherence | Security Officer | Open